GroupTrack

V3.0 Implementation Plan — Separated Build Strategy

March 29, 2026  |  Branch: feature/convoy-event-ride  |  Gate: Wednesday Field Test

# 1. Executive Summary

GroupTrack V3.0 migrates from a fully offline standalone app to a cloud-assisted platform. The migration must be built in two completely isolated phases with a hard gate between them — V2.4 Wednesday field test confirmation — to ensure the proven offline radio engine is never destabilized by backend integration work.

The core principle: build everything that has no device dependency first. Schema, service layer, sign-in screen, and API wiring are all safe to build now. The single connection point — replacing the existing ride creation flow with an API-backed version — is the last thing wired, and only after Wednesday confirms V2.4 is solid.

# 2. Architecture — What Changes and What Doesn't

## 2.1 Unchanged in V3.0

| COMPONENT | REASON UNCHANGED |
| --- | --- |
| Radio write engine | ConvoyProfileBuilder, InstallProfileUseCase, channel write — all V2.4. WorkingConfig source changes (local → downloaded JSON) but merge logic is identical. |
| Mesh radio operation | All mesh, GPS tracking, HUD, map display, and node tracking is purely offline. No V3.0 change touches any of this. |
| master.cfg binary | Stays in assets. Not hosted in RDS. Not modified by V3.0. |
| Offline map tile system | ConvoyTileDownloader, shouldInterceptRequest, convoy:// scheme — unchanged. V3.0 adds automated trigger, not new downloader. |
| Developer settings gate | Long press header → hardcoded password. Completely independent of Google Sign-In. Do not entangle these two auth systems. |
| Local JSON cache structure | convoy_events/{UUID}.json format unchanged. Downloaded rides save here identically to .convoy email imports. |

## 2.2 What V3.0 Adds

| NEW COMPONENT | DESCRIPTION |
| --- | --- |
| RDS Schema | 4 tables: users, rides, invites, enrollments. Created on EC2/RDS before any Android work. |
| PHP Service Layer | convoy_api.php already live. Endpoints: POST /users/register, POST /rides, POST /rides/{id}/invite, GET /ride/{token}, POST /enroll. |
| ConvoySignInScreen.kt | New screen. Google One Tap auth. POSTs to /users/register on success. Caches user_id in SharedPreferences. Not yet wired into navigation. |
| ConvoyApiClient.kt | New file. OkHttp wrapper for all API calls. No business logic — pure HTTP. Isolated, testable, not wired to UI until Phase 2. |
| API_BASE_URL in ConvoyConfig | const val API_BASE_URL = "http://34.224.89.217/" — one line, no functional impact. |
| Invite deep link handler | AndroidManifest intent-filter for grouptrack.org/invite/. Extracts token, calls GET /ride/{token}, saves JSON to convoy_events/. |

## 2.3 The Single Connection Point

There is exactly one place where V3.0 wires into existing V2.4 code: the ride creation flow. In V2.4, Create a Ride saves a local JSON file. In V3.0, it POSTs to /rides and saves the response to local cache. Everything downstream — WorkingConfig, radio write, RIDE tab display — is identical because both versions produce the same local JSON.

⚠  This connection point is ONLY wired after Wednesday test confirms V2.4 is stable. All other V3.0 work is built in isolation before that gate.

# 3. Phase 1 — Isolated Build (Safe Now, No Device Risk)

Everything in Phase 1 can be built immediately. None of these tasks touch existing V2.4 screens, ViewModel state, or the radio engine. If Phase 1 code has a bug, it has zero impact on the working V2.4 build.

## 3.1 Backend — RDS Schema

Task B-01 — Create RDS Schema

| ITEM | DETAIL |
| --- | --- |
| What | Run create_schema.sql against convoy_tracker database on RDS. Creates 4 tables: users, rides, invites, enrollments with all foreign keys. |
| Where | EC2 SSH session → mysql -h convoy-tracker-db.cudtjxrtdbql.us-east-1.rds.amazonaws.com -u convoy_admin -p convoy_tracker < create_schema.sql |
| Verify | SHOW TABLES; — expect 4 rows. DESCRIBE users; DESCRIBE rides; — confirm columns match spec. |
| Risk | NONE — pure database, no Android code |
| Est. | 30 minutes |

Task B-02 — Verify PHP API Endpoints

| ITEM | DETAIL |
| --- | --- |
| What | Confirm all 5 endpoints return expected responses after schema is created. Test with curl from Git Bash. |
| Test | curl -X POST http://34.224.89.217/users/register -H "Content-Type: application/json" -d '{"google_id":"test123","email":"test@test.com","first_name":"Fred","last_name":"Test"}' |
| Expect | JSON response with user_id UUID. Verify row appears in RDS: SELECT * FROM users; |
| Risk | NONE — server-side only, no app impact |
| Est. | 20 minutes |

## 3.2 Android — New Files Only (Zero Touch to Existing Code)

Task A-01 — Add API_BASE_URL to ConvoyConfig.kt

| ITEM | DETAIL |
| --- | --- |
| What | Add const val API_BASE_URL = "http://34.224.89.217/" to ConvoyConfig.kt. |
| File | app/src/main/java/com/geeksville/mesh/convoy/ConvoyConfig.kt |
| Impact | One line addition to an existing constants file. No behaviour change. Nothing calls it yet. |
| Risk | NONE |
| Est. | 5 minutes |

Task A-02 — Create ConvoyApiClient.kt (New File)

| ITEM | DETAIL |
| --- | --- |
| What | New file. OkHttp-based API client. Suspend functions for each endpoint. No UI dependency. No ViewModel dependency. |
| File | app/src/main/java/com/geeksville/mesh/convoy/ConvoyApiClient.kt — NEW |
| Functions | registerUser(googleIdToken), createRide(rideData), createInvite(rideId), downloadRide(token), enrollRider(rideId). Each returns Result<T>. |
| Impact | New file only. Not imported by any existing file. Zero risk to V2.4 operation. |
| Risk | NONE — new file, not referenced by anything yet |
| Est. | 1.5 hours |

Task A-03 — Create ConvoySignInScreen.kt (New File)

| ITEM | DETAIL |
| --- | --- |
| What | New Compose screen. Google One Tap integration. On success: calls ConvoyApiClient.registerUser(), caches user_id + google_id + name in SharedPreferences. |
| File | app/src/main/java/com/geeksville/mesh/convoy/ConvoySignInScreen.kt — NEW |
| Dependency | Add to build.gradle: com.google.android.gms:play-services-auth:21.x.x — already listed in V3 Architecture Plan. |
| Navigation | NOT yet wired into nav graph. Screen exists but is not reachable from the app. Tested directly via unit test or temporary debug entry point only. |
| Impact | New file + one build.gradle line. No existing screen or ViewModel touched. |
| Risk | NONE — unreachable screen cannot break existing flow |
| Est. | 2.5 hours |

Task A-04 — Add Invite Deep Link Handler

| ITEM | DETAIL |
| --- | --- |
| What | Add intent-filter to AndroidManifest for grouptrack.org/invite/ deep links. Handler extracts token, calls GET /ride/{token}, saves JSON to convoy_events/ using existing import handler. |
| Files | AndroidManifest.xml (intent-filter only) + new ConvoyInviteHandler.kt for token extraction and ride download logic. |
| Safe boundary | Downloaded ride JSON is saved to convoy_events/ identically to a .convoy email import. The existing import handler processes it. No new code path for ride loading. |
| Risk | LOW — AndroidManifest change requires careful testing. Deep link must not intercept unrelated URLs. |
| Est. | 1.5 hours |

Task A-05 — Lead Lock UI Buttons

| ITEM | DETAIL |
| --- | --- |
| What | Add SET AS LEAD button to NODE panel. Add I AM LEAD and RECALC LEAD buttons to MY CART panel. Logic already committed — buttons are UI only. |
| File | ConvoyScreen.kt only. Calls viewModel.setExplicitLead() and viewModel.recalcLead() — both already exist. |
| Risk | LOW — touches ConvoyScreen.kt which is the main screen. Must build and test before Wednesday. |
| Est. | 1.5 hours |

# 4. Wednesday Gate — V2.4 Field Test

This is a hard gate. Phase 2 wiring does not begin until all Wednesday tests pass. The gate exists to protect the proven offline radio engine from being destabilized by backend integration.

| # | ID | Test | Gate Status |
| --- | --- | --- | --- |
| 1 | FT-01 | Lead lock — drive 1/4 mile after RECORD, verify lead locks, single clean track line on switchbacks. | PENDING |
| 2 | FT-01B | SET AS LEAD, I AM LEAD, RECALC LEAD buttons — verify all three overrides work correctly. | PENDING |
| 3 | FT-04 | Offline maps render cleanly at z18 across downloaded SAT area. No grey patches. | PENDING |
| 4 | FT-05 | Maps render full screen at all zoom levels. No half-screen or spotty tile display. | PENDING |
| 5 | FT-06 | Auto-pan — zoom and pan do not snap back. Search result stays centered. GROUP/MY CART re-centers correctly. | PENDING |
| 6 | FT-02 | Channel utilization stable at 23-25% with 5 nodes. Lead at 3s interval, others at 5s. | VALIDATED — no retest needed |
| 7 | FT-03 | Bluetooth stability with Unrestricted battery setting. No timeout during ride. | DOCUMENTED — workaround in place |

⚠  If FT-04 or FT-05 fail, offline maps must be resolved before Phase 2 begins. Do not start RDS wiring on a build with broken offline maps.

# 5. Phase 2 — Integration Wiring (Post-Wednesday Only)

Phase 2 wires the isolated Phase 1 components into the existing V2.4 app. Each task has a clearly defined connection point — the exact line of code or screen where the new component touches existing code for the first time.

## 5.1 Wire Sign-In into App Launch

| ITEM | DETAIL |
| --- | --- |
| Connection point | MainActivity.kt or ConvoyScreen.kt LaunchedEffect on startup — check SharedPreferences for cached user_id. If missing, navigate to ConvoySignInScreen. |
| Key rule | If sign-in fails or is unavailable, app proceeds to main map anyway. Organizer features show a 'Sign in required' banner. Radio operation is never blocked. |
| Files touched | MainActivity.kt or top-level nav graph — single if-check addition. ConvoySignInScreen already built in Phase 1. |
| Risk | MEDIUM — touches app entry point. Must not block offline operation. |
| Est. | 1 hour |

## 5.2 Wire Ride Creation to POST /rides

| ITEM | DETAIL |
| --- | --- |
| Connection point | ConvoyViewModel.kt createRide() function — replace local JSON write with ConvoyApiClient.createRide() POST. On success, write API response to convoy_events/ as local JSON cache. |
| Fallback | If API call fails (offline), fall back to local-only ride creation. User sees a banner: 'Ride saved locally — will sync when online'. Radio write still works. |
| V2.4 compatibility | Rides created in V2.4 remain valid. eventId UUID is preserved as rides.ride_id. Existing .convoy files continue to work unchanged. |
| Risk | MEDIUM — touches createRide() in ViewModel. Fallback path must be solid before wiring. |
| Est. | 1.5 hours |

## 5.3 Wire Invite Generation and Share Sheet

| ITEM | DETAIL |
| --- | --- |
| Connection point | Ride detail screen — add SEND INVITE button. Calls ConvoyApiClient.createInvite(rideId). Opens Android ACTION_SEND share sheet with invite URL. |
| URL format | http://grouptrack.org/invite/{token} — links back to deep link handler built in Phase 1 Task A-04. |
| Risk | LOW-MEDIUM — new button on existing screen. Isolated API call. |
| Est. | 1 hour |

## 5.4 Wire Automated Map Download on Invite Accept

| ITEM | DETAIL |
| --- | --- |
| Connection point | ConvoyInviteHandler.kt (Phase 1 Task A-04) — after saving ride JSON, check if map_bounds_north/south/east/west are set. If yes, call ConvoyTileDownloader.downloadTiles() for the ride area. |
| Organizer setup | Ride creation screen gains the existing DOWNLOAD REGION draw tool in a new context. Drawn bounds are stored in rides table via POST /rides. |
| Risk | LOW — uses existing tile downloader. New trigger only. |
| Est. | 1.5 hours |

# 6. Full Task Sequence — Ordered Build Plan

| # | Phase | ID | Task | Est. | Risk |
| --- | --- | --- | --- | --- | --- |
| 1 | Backend | B-01 | Create RDS schema — run create_schema.sql. 4 tables: users, rides, invites, enrollments. | 30 min | NONE |
| 2 | Backend | B-02 | Verify PHP endpoints with curl — POST /users/register → confirm RDS row created. | 20 min | NONE |
| 3 | Android | A-01 | Add API_BASE_URL to ConvoyConfig.kt. One line. | 5 min | NONE |
| 4 | Android | A-02 | Create ConvoyApiClient.kt — OkHttp wrapper for all endpoints. New file only. | 90 min | NONE |
| 5 | Android | A-03 | Add Google Sign-In dependency to build.gradle. | 10 min | NONE |
| 6 | Android | A-04 | Build ConvoySignInScreen.kt — Google One Tap, POST /users/register, cache user_id. NOT wired to nav yet. | 2.5 hrs | NONE |
| 7 | Android | A-05 | Add invite deep link handler — AndroidManifest intent-filter + ConvoyInviteHandler.kt. GET /ride/{token} → save to convoy_events/. | 90 min | LOW |
| 8 | Android | A-06 | Lead Lock UI buttons — SET AS LEAD (NODE panel), I AM LEAD + RECALC LEAD (MY CART panel). Logic already committed. | 90 min | LOW |
| 9 | Android | A-07 | Build and install. Full regression test of all V2.4 features before Wednesday. | 30 min | LOW |
| ⚠ WEDNESDAY GATE — All FT tests must pass before proceeding to Phase 2 |  |  |  |  |  |
| 10 | Phase 2 | W-01 | Wire sign-in check into app launch — check SharedPreferences for user_id, navigate to ConvoySignInScreen if missing. | 1 hr | MED |
| 11 | Phase 2 | W-02 | Test sign-in end to end — sign in → POST /users/register → RDS row created → user_id cached → app proceeds to map. | 30 min | MED |
| 12 | Phase 2 | W-03 | Wire ride creation to POST /rides — replace local-only save with API call + local cache. Add offline fallback. | 90 min | MED |
| 13 | Phase 2 | W-04 | Wire invite generation — SEND INVITE button → POST /rides/{id}/invite → share sheet with invite URL. | 1 hr | LOW |
| 14 | Phase 2 | W-05 | Test invite flow end to end — organizer sends invite → rider taps link → app opens → ride downloaded → radio write succeeds. | 1 hr | MED |
| 15 | Phase 2 | W-06 | Wire automated map download on invite accept — check map_bounds in ride JSON → trigger ConvoyTileDownloader. | 90 min | LOW |
| 16 | Phase 2 | W-07 | Full V3.0 end-to-end test — sign in, create ride with map area, send invite, rider accepts, tiles auto-download, radio write, mesh operation. | 1 hr | MED |

# 7. Separation Rules — What Must Never Be Crossed

These rules enforce the isolation between Phase 1 and Phase 2. They protect V2.4 stability during the build period before Wednesday.

| RULE | RATIONALE |
| --- | --- |
| ConvoySignInScreen must NOT be in the nav graph until Phase 2 Task W-01 | An unreachable screen cannot break launch flow. The moment it is wired in, every app start depends on it. |
| ConvoyApiClient must NOT be called from any existing ViewModel until Phase 2 | All existing ViewModel code operates offline. Introducing network calls before Wednesday risks timeouts and crashes during field test. |
| createRide() must NOT call the API until Phase 2 Task W-03 | The existing ride creation flow is proven working. Do not touch it until Wednesday confirms V2.4 is solid. |
| build.gradle Google Sign-In dependency may be added in Phase 1 — it is a library, not a code path | Adding a dependency to build.gradle has zero runtime impact if nothing calls it. Safe to add any time. |
| AndroidManifest deep link intent-filter is safe in Phase 1 if handler gracefully no-ops when user_id is missing | A deep link that silently does nothing when prerequisites aren't met cannot break the existing app. |
| Radio write engine, ConvoyProfileBuilder, and InstallProfileUseCase must NOT be touched at all in V3.0 | The radio write process is the most complex proven component. V3.0 only changes where ride JSON originates, not how it is applied. |

# 8. Environment Reference

| ITEM | VALUE |
| --- | --- |
| Branch | feature/convoy-event-ride |
| EC2 IP | 34.224.89.217 — convoy-api-server |
| EC2 SSH | ssh -i ~/.ssh/convoy-api-key-2.pem ec2-user@34.224.89.217 |
| RDS Endpoint | convoy-tracker-db.cudtjxrtdbql.us-east-1.rds.amazonaws.com |
| RDS Database | convoy_tracker / convoy_admin |
| API Base URL | http://34.224.89.217/ |
| API File (EC2) | /var/www/html/convoy_api.php |
| Web Root | /var/www/html/ |
| Website | http://grouptrack.org — LIVE |
| Device 1 | 8624SBCEDF00001789 — primary test device |
| Device 2 | 24039703201775 |
| Key pair | ~/.ssh/convoy-api-key-2.pem |
| Google Play Services dep | com.google.android.gms:play-services-auth:21.x.x |

GroupTrack  |  V3.0 Implementation Plan  |  March 29, 2026  |  CONFIDENTIAL