GroupTrack

Thursday — Phase B Work Sequence

Post Wednesday Field Test  |  Branch: feature/convoy-event-ride  |  V3.0 Phase B

⚠  Do not begin this work until Wednesday field test confirms all 8 tests pass.

⚠  Execute tasks in exact sequence. Each task builds on the previous. Do not skip ahead.

# Block 1 — Wednesday Night Post-Test Fixes

Fix any failures from Wednesday field test before beginning Phase B. These run Wednesday night after returning from the field.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | WN-01 | Fix any FT failures from Wednesday field test | TBD |
| ☐ | WN-02 | Rebuild User Guide V2.4 PDF with all confirmed V2.4 features | 30 min |
| ☐ | WN-03 | Commit all Wednesday night fixes before beginning Phase B | 5 min |

# Block 2 — RideState Wiring (Phase B First Priority)

RideState must be wired and tested before any new screens are built. Every new screen references RideState.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-01 | Apply RideState tick computation to ConvoyViewModel.kt — channelSetFlow read + ConvoyEventStore match. patch_ride_state_v3.py ready. | 20 min |
| ☐ | PB-02 | Verify RideState computes correctly — logcat shows SOLO/CONVOY/ORGANIZED on each tick | 10 min |
| ☐ | PB-03 | Add SOLO trail display branch in ConvoyScreen.kt — if rideState == SOLO use gpsTrailSegments as primary display | 30 min |
| ☐ | PB-04 | Add queueSurvey() function to ConvoyViewModel.kt — stores survey answers + track donation to SharedPreferences queue | 30 min |
| ☐ | PB-05 | Apply survey dialog patch to ConvoyScreen.kt showNameDialog — ORGANIZED gets survey+name, SOLO/CONVOY gets simple name dialog. patch_survey_dialog.py ready. | 30 min |
| ☐ | PB-06 | Build and install — verify both dialogs show correctly based on RideState | 10 min |
| ☐ | PB-07 | Commit: feat: V3 Phase B — RideState wired, survey dialog, SOLO trail display | 5 min |

# Block 3 — Schema ALTER TABLE

Run all new column additions against RDS before building screens that reference them. All nullable — zero impact on existing data.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-08 | SSH to EC2. Run ALTER TABLE rides ADD COLUMN start_time, trailhead_lat, trailhead_lon, trailhead_name, latitude, longitude | 10 min |
| ☐ | PB-09 | Run ALTER TABLE users ADD COLUMN default_radius_miles, latitude, longitude, fcm_token, fcm_token_updated | 10 min |
| ☐ | PB-10 | Run ALTER TABLE ride_tracks ADD COLUMN bounds_north, bounds_south, bounds_east, bounds_west | 5 min |
| ☐ | PB-11 | Verify all columns: DESCRIBE rides; DESCRIBE users; DESCRIBE ride_tracks; | 5 min |

# Block 4 — SSL on EC2

Required before any Google Sign-In token travels the wire. Must be done before sign-in is wired.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-12 | SSH to EC2: sudo yum install certbot python3-certbot-apache -y | 5 min |
| ☐ | PB-13 | Run: sudo certbot --apache — follow prompts for grouptrack.org | 10 min |
| ☐ | PB-14 | Update API_BASE_URL in ConvoyConfig.kt from http:// to https://34.224.89.217/ or https://grouptrack.org/ | 5 min |
| ☐ | PB-15 | Test HTTPS endpoint with curl — confirm API responds over SSL | 5 min |

# Block 5 — Sign-In Wiring

Wire ConvoySignInScreen into the app launch flow. Check for user_id on start — if missing navigate to sign-in.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-16 | Add ConvoySignIn composable to ConvoyNavigation.kt nav graph | 20 min |
| ☐ | PB-17 | Add launch check — if user_id missing navigate to ConvoySignIn. If offline proceed to map with banner. | 30 min |
| ☐ | PB-18 | Test sign-in E2E — sign in → POST /users/register → RDS row → user_id cached → app proceeds | 20 min |
| ☐ | PB-19 | Wire rider + privacy terms screens to first launch flow. Both must be accepted. Version tracked. | 45 min |
| ☐ | PB-20 | Build and install — full sign-in + terms flow tested on device | 10 min |
| ☐ | PB-21 | Commit: feat: V3 Phase B — sign-in wired, terms flow, launch check | 5 min |

# Block 6 — Dashboard + Field Radio Screens

Build Dashboard and Field Radio as new isolated screens. Wire to GroupTrack button entry point.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-22 | Build ConvoyDashboardScreen.kt — 5 buttons, notifications panel, internet gate (grey buttons if offline), RideState indicator | 2 hr |
| ☐ | PB-23 | Build ConvoyFieldRadioScreen.kt — Radio Config access only, always active, no internet needed | 45 min |
| ☐ | PB-24 | Add DASHBOARD and FIELD RADIO buttons to GroupTrack entry point in Meshtastic nav | 45 min |
| ☐ | PB-25 | Build and install — Dashboard and Field Radio accessible, internet gate working | 10 min |
| ☐ | PB-26 | Commit: feat: V3 Phase B — Dashboard, Field Radio, GroupTrack nav entry point | 5 min |

# Block 7 — New Screen Builds (Rides Section)

Build all new screens as isolated files using GroupTrackTheme. Wire into Dashboard navigation. These replace existing V2.4 event screens in Phase B.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-27 | Build ConvoyRidesScreen.kt — My Rides list, upcoming first, CREATE NEW RIDE button, organizer gated | 90 min |
| ☐ | PB-28 | Build ConvoyCreateRideScreen.kt — all fields: name, date, start time, trailhead, map bounds, route, visibility, channel | 2 hr |
| ☐ | PB-29 | Build ConvoyRideDetailScreen.kt — enrolled list, conditional buttons (private=invite, public=broadcast) | 90 min |
| ☐ | PB-30 | Build ConvoyInviteSendScreen.kt — QR code, copy link, share sheet. Private rides only. | 60 min |
| ☐ | PB-31 | Build ConvoyBroadcastScreen.kt — follower count, email count, one-time confirmation. Public rides only. | 45 min |
| ☐ | PB-32 | Build ConvoyRideConfirmScreen.kt — invite acceptance screen: ride name, organizer, date, time, trailhead, status checklist | 60 min |
| ☐ | PB-33 | Wire all Rides screens into Dashboard nav. Test ride creation E2E — create → invite → accept → radio config | 45 min |
| ☐ | PB-34 | Commit: feat: V3 Phase B — Rides section screens wired | 5 min |

# Block 8 — Survey Upload Worker

Process queued surveys on connectivity. Runs in background on app launch.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-35 | Add survey upload worker to ConvoyViewModel — check SharedPreferences queue on launch, POST /ride/survey for each pending, clear on success | 45 min |
| ☐ | PB-36 | Test survey queue — fill out survey offline, reconnect, confirm survey uploads and clears from queue | 15 min |

# Block 9 — Full E2E Test

Complete end-to-end test of all three RideStates and the full V3.0 invite flow before declaring Phase B complete.

|  | ID | Task | Est. |
| --- | --- | --- | --- |
| ☐ | PB-37 | SOLO state — no radio, record track, stop, confirm simple dialog, GPX saved to device | 10 min |
| ☐ | PB-38 | CONVOY state — two radios, no ride loaded, confirm convoy HUD, simple dialog on stop | 10 min |
| ☐ | PB-39 | ORGANIZED state — create ride, send invite, accept on device 2, radio config applies, convoy active, survey dialog on stop, track donation | 30 min |
| ☐ | PB-40 | Confirm RDS data — ride row, enrollment row, survey row, ride_tracks row if donated | 10 min |
| ☐ | PB-41 | Commit: feat: V3 Phase B complete — all three RideStates proven, full invite flow E2E | 5 min |

| THURSDAY TOTAL ESTIMATE | ~12 HOURS — FULL SESSION |
| --- | --- |

★  Phase B is complete when Block 9 E2E test passes clean. Phase C (Google Play + payments) begins next session.

★  New screen builds in Block 7 can be split across multiple sessions if needed. Blocks 1-6 must complete in one session.

GroupTrack  |  Thursday Phase B Sequence  |  Post Wednesday Gate  |  Branch: feature/convoy-event-ride