GroupTrack

Friday Session Reference

V2.4 Play Store Publish + V2.5 Release Planning & Sequencing

May 1, 2026  |  Confidential — Internal Development

# PART 1: Current State (April 30 EOD)

## 1.1 Play Store Status

| Item | Value | Status |
| --- | --- | --- |
| Package | com.grouptrack.android | DONE |
| Live AAB on Play Store | 29320449 (no storage fix) | NEEDS REPLACE |
| New AAB built | 29320455 in ~/Downloads | READY |
| App Content Checklist | All items complete | DONE |
| Store Listing Text | Name, short desc, full desc | DONE |
| Screenshots | Not captured yet | NOT DONE |
| Testers Enrolled | Fred only — need 12 | NOT DONE |
| Privacy Policy | grouptrack.org/privacy.html | DONE |
| Terms of Service | grouptrack.org/terms.html | DONE |

## 1.2 V2.4 Code Status

| Item | Status | Notes |
| --- | --- | --- |
| Storage permissions | FIXED | Uncommented + tools:node=replace |
| My Cart !phone identity | FIXED | Phone-only mode correct |
| z18 bypass | FIXED | SHOW_DOWNLOADED_ON_OPEN=false |
| SHOW DOWNLOADED hardening | FIXED | Progress + disable in both screens |
| Location permission (bg) | FIXED | bgLocationLauncher added |
| Storage runtime permissions | FIXED | MANAGE_EXTERNAL_STORAGE request |
| Autopause | REVERTED | ANR in phone-only tick loop → V2.5 |
| Track picker layout | STASHED | git stash — fix plan in docx |
| BLE dropout | OPEN | Hardware issue on budget devices |

# PART 2: Friday Immediate Tasks

Complete these actions Friday to advance the Play Store pipeline.

## 2.1 Upload AAB 29320455 to Play Console

The new AAB with the storage permission fix is built and in ~/Downloads. It replaces the broken 29320449.

- Play Console → Internal Testing → Create new release

- Upload app-google-release.aab (version 29320455)

- Release notes: "Storage permission fix, background location permission, show-downloaded hardening"

- Save and publish to internal test track

## 2.2 Capture Store Listing Screenshots

Required before promoting to closed testing. Capture 2–3 from Android 1:

- Convoy map with trail overlay visible

- Tile download manager screen

- Track list / My Tracks view

Capture command:

adb -s 8624SBCEDF00001789 exec-out screencap -p > ~/Downloads/screen1.png

## 2.3 Begin Tester Recruitment

Closed testing requires minimum 12 testers opted in for 14 consecutive days.

- Riding group contacts — people who will field test on actual rides

- Each tester needs a Google account and must opt in via the Play Store test link

- The 14-day clock starts when the 12th tester opts in

# PART 3: Play Store Pipeline — V2.4 to Production

| # | Step | Timeline | Status |
| --- | --- | --- | --- |
| 1 | Upload AAB 29320455 | Friday May 1 | TODO |
| 2 | Screenshots for store listing | Friday May 1 | TODO |
| 3 | Verify internal test install works | Friday May 1 | TODO |
| 4 | Recruit 12 testers | May 1–7 | TODO |
| 5 | Promote to closed testing | When 12 testers enrolled | BLOCKED |
| 6 | 14-day closed test window | ~May 7–21 (est.) | BLOCKED |
| 7 | Apply for production access | ~May 22 | BLOCKED |
| 8 | Google review + production launch | ~May 25–30 (est.) | BLOCKED |

Critical path: Tester recruitment. The 14-day clock does not start until 12 testers opt in.

# PART 4: V2.5 Release Planning

V2.5 development runs parallel with the V2.4 closed test window. The 14-day mandatory wait is the build window.

## 4.1 V2.5 Bug Fixes (from V2.4 open items)

| ID | Issue | Priority | Notes |
| --- | --- | --- | --- |
| ANR-01 | Phone-only ANR — autopause tick loop | P1 GATE | Built+reverted V2.4. Async trail ANR in phone-only tick. Must fix. |
| PICK-01 | Track picker layout conflict | P2 | Stashed. Fix plan: Option A mutual exclusion. |
| BLE-01 | BLE scan button missing on resume | P2 | Reset GATT registration on lifecycle. |
| BLE-02 | Radio requires power cycle | P2 | Same root cause as BLE-01. |

## 4.2 V2.5 New Map Functions (from Planning v2)

| ID | Function | Priority | Notes |
| --- | --- | --- | --- |
| MAP-01 | GPS recording 1s interval | P1 | ConvoyGpsService.kt:249 — 3000L to 1000L |
| MAP-02 | Lead cart 5-point broadcast | P1 | New file. 86-byte PRIVATE_APP packet. |
| MAP-03 | KML/GPX route overlay | P1 | Leaflet omnivore. File picker. JS bridge. |
| GPS-01 | Standalone GPS track recording | P2 | Android GPS when no radio connected. |
| GPS-02 | Standalone mode — My Cart as lead | P2 | No radio = My Cart is lead by default. |
| MAP-07 | Waypoint management | P2 | Drop pins, name, persist, show on map. |

## 4.3 V2.5 Scope Decision (decide Friday)

Two options for V2.5 scope:

- Option A — Bug-fix-only: ANR-01 + PICK-01 + BLE fixes. Small scope. Ships during closed test window. Map features become V2.6.

- Option B — Feature release: Bug fixes + MAP-01/02/03 + GPS-01/02. Larger scope. May extend past the closed test window.

Recommendation: Option A. Gets a clean production release faster. The 14-day window is tight for the full MAP feature set, and shipping bugfixes sooner de-risks the tester experience.

## 4.4 Package Migration Note

V2.5 Planning docs call out package migration from com.geeksville.mesh to com.grouptrack.android. This is already done for the Play Store build (com.grouptrack.android). The tile storage path migration (to /sdcard/GroupTrack/tiles/) is still pending and could ride in V2.5 if scoped as bug-fix-only, or defer to V2.6 with the map features.

# PART 5: V2.5 Build & Publish Sequence

## 5.1 Pre-Build Checklist

- Confirm V3_FEATURES_ENABLED = false in ConvoyConfig.kt

- Bump versionCode in app/build.gradle.kts (must be > 29320455)

- Run sync_assets_v1.sh for pre-build asset sync

- Commit all changes — clean working tree

- Tag: git tag v2.5-YYYYMMDD -m "V2.5 release"

## 5.2 Build Commands

Release AAB (Play Store):

./gradlew bundleGoogleRelease -x uploadCrashlyticsMappingFileGoogleRelease

Release APK (local smoke test):

./gradlew assembleGoogleRelease -x uploadCrashlyticsMappingFileGoogleRelease

Smoke test on Android 1:

adb -s 8624SBCEDF00001789 install -r -d app/build/outputs/apk/google/release/app-google-release.apk

## 5.3 Play Store Upload

- cp app/build/outputs/bundle/googleRelease/app-google-release.aab ~/Downloads/

- Play Console → Internal Testing → Create new release → Upload AAB

- Add V2.5 release notes

- Save and publish

If V2.4 closed testing is already running, uploading a new AAB to the same track updates the build for existing testers without restarting the 14-day clock (unless Google flags a policy issue on review).

# PART 6: Supporting Deliverables

| Deliverable | Status | Notes |
| --- | --- | --- |
| Store listing screenshots | TODO | 2–3 from Android 1. Map, tiles, tracks. |
| User manual PDF | TODO | Basic workflow for testers. |
| Install guide | TODO | Side-load APK or Play Store opt-in. |
| Device compatibility list | TODO | Document BLE budget device limitation. |
| Tester invite template | TODO | Email/text for recruiting 12 testers. |

# PART 7: Quick Reference

## 7.1 Build & Install Commands

| Command | Value |
| --- | --- |
| Debug APK | ./gradlew copyApkToDownloads |
| Release APK | ./gradlew assembleGoogleRelease -x uploadCrashlyticsMappingFileGoogleRelease |
| Release AAB | ./gradlew bundleGoogleRelease -x uploadCrashlyticsMappingFileGoogleRelease |
| Install Android 1 | adb -s 8624SBCEDF00001789 install -r -d [apk] |
| Install Android 2 | adb -s 24039703201775 install -r -d [apk] |
| Screenshot | adb -s 8624SBCEDF00001789 exec-out screencap -p > ~/Downloads/screen.png |

## 7.2 Key Paths

| Item | Path |
| --- | --- |
| Project root | ~/Meshtastic-Android |
| ConvoyConfig | app/src/main/java/com/geeksville/mesh/convoy/ConvoyConfig.kt |
| Build gradle | app/build.gradle.kts |
| AAB output | app/build/outputs/bundle/googleRelease/app-google-release.aab |
| APK output | app/build/outputs/apk/google/release/app-google-release.apk |
| Keystore props | ~/Meshtastic-Android/keystore.properties (NEVER commit) |
| Track picker fix | GroupTrack_ConvoyTrackPickerFixPlan_v1.docx |
| V2.5 planning | GroupTrack_V25_Planning_v2.docx |

## 7.3 Signing Note

Play Store and local APK have different signing keys. Must uninstall one before installing the other. Play Store app (com.grouptrack.android) from test link cannot coexist with a locally-signed debug APK on the same device.

## 7.4 Stashed Work

Track picker layout conflict:

git stash save "track picker layout conflict - fix tomorrow"

Last clean commit before stash: 9d66c9781

GroupTrack  |  Friday Session Reference  |  May 1, 2026  |  Prepared April 30 EOD